## Sheet1
ID | Module | Task | Estimated time needed
1 | Shift selection | Module to select shift for each team leader, shift change option will be provided to the team from this module | 1 day
2 | Calender | Remove shift change displayed in the calender | 1 hour
3 | Attendance report | Provide report for attendance (Individual, team, shift and company) | 1 & half day
4 | Leave status report | Provide leave status report for (Individual, team, shift and company) | 1 & half day
5 | Break exceed approval module | Provide option to approve break exceed, display employees with working time between 7:19 - 7:10 and option to add time allowed for break | 1 day
6 | Calendar > self | Display break exceed and late coming for self calendar with time and deduction | 3 Hours
7 | Attendance | Display additional breaks till 5 breaks | 1/2 day
8 | Deligation | Module to delegate task for team and manager when they are not leave | 1 week