## Sheet1
ID | Module | Task | Estimated time needed
1 | Attendance Report | Make different reports for Attendance and summery | 1/2 day | done | 2013-03-29
2 | Attendance Report | Display approved exceed and late coming in attendance report | 1/2 day |  | 2013-03-30
3 | Workhours approval | Temporary comment time allowance | 30 Mins | done | 2013-03-29
4 | Attendance Report | Display breakexceed with different color and exceed time in tooltip | 1 Hour | done | 2013-03-29
5 | Attendance Report | Change caption of the Year |  | done | 2013-03-29
6 | Leave History | Link to attendance and not leaves | 1 day
7 | Self calendar | Display break exceed in 2 lines |  | done | 2013-03-29
8 | Leave Management | If leave unapproved by team leader do not send for manager approval | 2 Hours | done | 2013-03-30
9 | Shift Movement | If shift movement un approved by team leader do not send for manager approval | 2 Hours | done | 2013-03-30
10 | Attendance > Add | Validate the time entered as per the shift time (4 hours from the shift start) | 1/2 day | done | 2013-03-30
11 | Help | Add help for all modules and add text "Help" with help image | 1/2 day