## Sheet1
ID | Task | Description | Status | Completed By | Notes
1 | User profile |  | COMPLETE | Gagan
2 | Role Management |  | COMPLETE | Chandni
3 | Shift movement management for attendence |  | COMPLETE | Chandni
4 | Validation on employee add |  | COMPLETE | Gagan
5 | Leave mail sending |  | COMPLETE | Gagan
6 | Calender for leaves |  | PENDING
7 | Leave form fill time pending leave counts |  | PENDING
8 | After approve remaining leave counts |  | Not to do
9 | Leave calculation for every month in other table |  | PENDING
MEETING CHANGES
1 | Eligible leaves - Leave balance + 7 | Modified it to +7 as informed by parvez sir | COMPLETE | Gagan
2 | Fill address and contact no in leave form |  | COMPLETE | Gagan
3 | Display employee on leave on the same day for leave approval | For TL & Managers & admin | COMPLETE | Gagan
4 | Display TL in Leave request list | For Manager & Admin | COMPLETE | Gagan
5 | Generate roaster - Saturday | Fill in the details showing present as per the leaves added till now. If the roaster is not submitted on Sunday 12 noon, auto generate the roaster with Sunday weekoff. One time process cannot update | COMPLETE | Chandni
6 | Remove time picker for attendence add module | Time will be entered in 4 digits / 3 digits, convert to time format | COMPLETE | Chandni
7 | Disable weekoff and public holidays in attendence add module |  | COMPLETE | Chandni
8 | Display leave balance on add leave form |  | COMPLETE | Gagan
9 | Display calendar instead of list for attendence |  | COMPLETE | Chandni
10 | Leave history | Display leave history for the leave approval. Display last 3 leaves | COMPLETE | Gagan
11 | History of team leaders and managers. | So that the previous work can be counted | PENDING
12 | History for shifts |  | PENDING
13 | Shift movement management |  | COMPLETE | Chandni
14 | Display calendar for all logins | Manager -> Their team and Agents, TL -> Agents, Agents -> Own | COMPLETE | Gagan
15 | Auto calculate dates / validate dates for no of days |  | COMPLETE | Gagan | Validation done for two dates and days that user enter
Meeting 28 Feb 2013
ID | Module | Task | Status | Completed By | Notes
1 | Leave Request | Change the caption "Last three leave requests" to "Leave history of EmployeeName" | COMPLETE | Gagan
2 | Leave Request | Change the caption "Leaves" to "Overall leave status of your team" | COMPLETE | Gagan
3 | Leave Form -> Add new leave form | Change the caption "Eligible leaves" to "Maximim leaves you can apply for" | COMPLETE | Gagan
4 | Leave Form -> Add new leave form | Do not display "Eligible leaves" in agent login | COMPLETE | Gagan
5 | Leave Form -> Add new leave form | Change the caption "Remaining Leaves" to "Leave balance" | COMPLETE | Gagan
6 | Attendance Calendar | Show Sunday as week off (Different color) | COMPLETE | Chandni
7 | Attendance Calendar | Show different attendance calendar for Team leader and his team | COMPLETE | Chandni
8 | Shift Movement -> Add shift movement | Provide dropdown for Hours, minutes and am/pm, for movement start and end time and compensation start and end time | COMPLETE | Chandni
9 | Shift Movement -> Add shift movement | Display movement start time as current time + 5 minutes | COMPLETE | Chandni
10 | Shift Movement -> Add shift movement | Change text for the alert message for the shift movement to "Shift movement not allowed for short notice. Please apply well in advance" | COMPLETE | Chandni
11 | Shift Movement -> Add shift movement | Shift movement for the current date can be added with in 1 hour of shift start | COMPLETE | Chandni
12 | Shift Movement -> Add shift movement | Cannot add shift movement if the compensation is not added for the shift movement | COMPLETE | Chandni
13 | Emergancy shift movement | Give option to Teamleader to add emergancy shift movement for the agents and Managers to added emergancy shift of the Teamleader . This can be added within the day of leave + 2 hours of the shift | COMPLETE | Chandni
14 | Shift movement compensation | Provide an option to added compensation for shift movement. Shift movement compensation of the agent is to be approved/unapproved by the team leader, and compensation for the team leader is to approved/unapproved by the manager | COMPLETE | Chandni
15 | Shift movement compensation | Auto populate compensation date to current date and, auto calculate from and to compensation time. To time should be current time. | COMPLETE | Chandni
16 | Roaster -> View roaster | Remove compensation information for the popup. | COMPLETE | Chandni
17 | Roaster -> View roaster | Change SC to P, display timing for the shift change | COMPLETE | Chandni
18 | Roaster -> View roaster | Display shift time for all the present date | COMPLETE | Chandni
19 | Roaster -> Add roaster | Display shift timings only for the team working in multiple shifts | COMPLETE | Chandni
20 | Roaster -> Add roaster | Display shift timings for SM and P | COMPLETE | Chandni
21 | Roaster print | Print/pdf option for the roaster. Display shift time for the same | COMPLETE | Chandni
Meeting 6 Mar 2013
ID | Module | Task | Status | Completed By | Notes
1 | Shift Movement Menu | Change caption "Users" to "Application" | COMPLETE | Chandni
2 | Public holiday module | Module to manage the public holiday | COMPLETE | Chandni
3 | Manage Roaster | Provide option to change public holidays to working day. This can be added as a leave for the current month. If leave is not taken for the current month, conver the public holiday to leave count | COMPLETE | TASK IN LEAVE MODULE COMPLETED BY GAGAN. TASK IN ROASTER COMPLETED BY CHANDNI
4 | Work deligation [for TL & manager on leave] | Provide an option in leave request form of manager to add deligation for the TL / Manager on leave. Leaves of the members under the TL / Manager can be approved for that particular period. | PENDING
Meeting 13 Mar 2013
ID | Module | Task | Estimated time needed
1 | Attendance > Add attendance | Add option to enter in time & outtime for 4th break | Friday | COMPLETE | Gagan
2 | Employee > Add employee | Add option to select Namaz option | Friday | NOT TO BE DONE
3 | Shift timings > Add shift timings | Provide option to add break time for namaz and option to select where namaz time is applied for the whole week / Friday | Friday | NOT TO BE DONE
4 | Calendar > Self | Display break exceed and late coming | Friday
5 | Work deligation [for TL & manager on leave] | Provide an option in leave request form of manager to add deligation for the TL / Manager on leave. Leaves of the members under the TL / Manager can be approved for that particular period. | 1 week
Meeting 14 Mar 2013
ID | Module | Task | Status | Completed By | Notes
1 | Shift selection | Module to select shift for each team leader, shift change option will be provided to the team from this module | COMPLETE | Chandni
2 | Calender | Remove shift change displayed in the calender | COMPLETE | Chandni
3 | Attendance report | Provide report for attendance (Individual, team, shift and company) | COMPLETE | Chandni
4 | Leave status report | Provide leave status report for (Individual, team, shift and company)
5 | Break exceed approval module | Provide option to approve break exceed, display employees with working time between 7:19 - 7:10 and option to add time allowed for break
6 | Calendar > self | Display break exceed and late coming for self calendar with time and deduction
7 | Attendance | Display additional breaks till 5 breaks | COMPLETE | Gagan
8 | Deligation | Module to delegate task for team and manager when they are not leave
Meeting 21 Mar 2013
ID | Module | Task | Status | Completed By | Estimated time needed
1 | Shift Time | Remove induction from team shift time | COMPLETE | Chandni | 5 Min
2 | Workhours Approval | Display reason in insufficient workhours [i.e show break exceed / latecomming] | COMPLETE | Chandni | 1 Hour
3 | Attendance report | Print option in attendance report | COMPLETE | Chandni | 2 Hours
4 | Attendance report | Display late time in tooltip | COMPLETE | Chandni | 30 Mins
5 | Leave report | Display leave history of the employee |  |  | 1 day
6 | Self calendar | Remove name from self calendar | COMPLETE | Chandni | 30 Mins
7 | Attendance report | Remove from date and to date and provide dropdown for month and year [year should be current and previous] | COMPLETE | Chandni | 1 Hour
8 | Attendance report | Display color indication | COMPLETE | Chandni | 30 Mins
9 | Emergency leave | Module to add emergency leave, this option is provided to the team leader & manager for their team | COMPLETE | Chandni | 1 day
10 | Leave & shift movement | Compulsory manager approval for shift movement and leave | COMPLETE | Gagan | 1 day
11 | Attendance add | Provide option to change shift change | COMPLETE | Chandni | 2 Hours
12 | Halfday leave module | Provide option to add halfday leave. Leave should be an option for first half and second half | COMPLETE | Gagan | 1 day
13 | Mails | Application for shift movement, leave and halfday leave. Roster reminder, Pending leaves to be approved
14 | Help module | Display help for each module